## Presidents Room
Kit	Prop	Desc	Status	Type		Design Time	Application Time	Station Prep	Cable Set	Installation	Testing & Drag.		Feb 10		Feb 11		Feb 12		Feb 13		Feb 14		Feb 15	Feb 16		Feb 17		Feb 18	Feb 19		Feb 20		Feb 21	Feb 22		Feb 23		Feb 24	Feb 25		Feb 26		Feb 27	Feb 28		Feb 29		Mar 1	Mar 2		Mar 3		Mar 4	Mar 5		Mar 6		Mar 7	Mar 8		Mar 9		Mar 10	Mar 11		Mar 12		Mar 13	Mar 14		Mar 15		Mar 16	Mar 17		Mar 18		Mar 19	Mar 20		Mar 21		Mar 22	Mar 23		Mar 24		Mar 25	Mar 26		Mar 27		Mar 28	Mar 29

FLEX	Flexmax 2 Show Controller			Forecast	39.5	10	20	2.5	5.5	1.5	0
		Mount & Secure	Complete	Actual	3	0.5		2		0.5
		Install 12VDC 5AMP Powersupply	Complete	Actual	0.75	0.25				0.5
		Connect Input #1		Actual	1.5	0.25	1		0.25
		Connect Input #2 - Trigger Lever Puzzle		Actual	1.5	0.25	1		0.25
		Connect Input #3		Actual	1.5	0.25	1		0.25
		Connect Input #4		Actual	1.5	0.25	1		0.25
		Connect Inout #5		Actual	1.5	0.25	1		0.25
		Connectr Input #6		Actual	1.5	0.25	1		0.25
		Connect Input #7		Actual	2.25	0.5	1	0.5	0.25
		Connect Input #8		Actual	1.5	0.25	1		0.25
		Connect Output #1		Actual	1	0.25	0.5		0.25
		Connect Output #2		Actual	1	0.25	0.5		0.25
		Connect Output #3		Actual	1	0.25	0.5		0.25
		Connect Output #4		Actual	1	0.25	0.5		0.25
		Connect Output #5		Actual	1	0.25	0.5		0.25
		Connect Output #6		Actual	1	0.25	0.5		0.25
		Connect Output #7		Actual	1	0.25	0.5		0.25
		Connect Output #8		Actual	1	0.25	0.5		0.25
		Connect Output #9 - Radar		Actual	1	0.25	0.5		0.25
		Connect Output #10 - Color Monitor		Actual	1	0.25	0.5		0.25
		Connect Output #11		Actual	1	0.25	0.5		0.25
		Connect Output #12		Actual	1	0.25	0.5		0.25
		Connect Output #13		Actual	1	0.25	0.5		0.25
		Connect Output #14		Actual	0.75	0.25	0.5
		Connect Output #15		Actual	0.75	0.25	0.5
		Connect Output #16		Actual	0.75	0.25	0.5
		Connect DMX OUT (RJ45)		Actual	0.75	0.25	0.5
		Build RJ45 Adapter		Actual	0.75	0.25	0.5
		Insert MP3 Audio Tracks		Actual	0.75	0.25	0.5
		Connect Audio Speakers		Actual	1.25	0.25	0.5			0.5
		Program Scenes		Actual	2.5	2	0.5
		Test Equipment		Actual	0
				Remaining	1.75	0	1.5	0	0.25	0	0

Console 1B	Radar Screen	Build Radar Screen Prop		Forecast	19.5	4.5	10	4.5	0.5
		Update Firmware		Actual	1	1	0	0
		Update Rasberian OS		Actual	1	1	0	0
		Design Webpage		Actual	0.5	0.5	0	0
		Locate and Upload Graphic Video		Actual	0.5	0.5	0	0
		Test monitor with Raspberry Pie		Actual	3.25	0.25	2	1
		Cut Window into Console		Actual	1.25	0.25	0	1
		Add blocking to support Monitor		Actual	1.25	0.25	0	1
		Install monitor into console		Actual	0.75	0.25		0.5
		Program Pie Startup to launch webpage full view		Actual	8.25	0.25	8
		Connect to Relay Board 4CH #1		Actual	1.75	0.25	0	1	0.5
				Remaining	0	0	0	0	0	0	0

Console 1	Relay Board 4CH #1	Assemble Relay Board for Monitors		Forecast	2.5	1	0	0.5	0.5	0.5
		Set-Up 4CH Relay Board #1 Controller		Actual	0.25	0.25
		Power Controller 12VDC Powersupply		Actual	0.75	0.25				0.5
		Connect to Outputs 9 & 10 Flexmaxx Cableset		Actual	0.75	0.25			0.5
		Mount & Secure		Actual	0.75	0.25		0.5
				Remaining	0	0	0	0	0	0	0

Room 1	Color Bar Screen	Build Color Bar Screen Prop		Forecast	12	2	6	3	0.5	0.5
		Update Firmware		Actual	1.25	0.25	1
		Update ./ssh & GIT		Actual	5.25	0.25	5
		Design Webpage		Actual	0.25	0.25
		Upload Graphic Video		Actual	0.25	0.25
		Test monitor with Raspberry Pie		Actual	0.25	0.25
		Cut Window into Console		Actual	2.25	0.25		2
		Add blocking to support Monitor		Actual	1.75	0.25		1		0.5
		Connect to DMX TRI RELAY BOARD		Actual	0.75	0.25			0.5
				Remaining	0	0	0	0	0	0	0

Room 1	Relay Board 4CH #2	Relay Board for Key Pads		Forecast	2.75	1	0	0.5	0.75	0.5	0
		Set-Up 4CH Relay Board #1 Controller		Actual	0.25	0.25			0	0
		Power Controller 12VDC Powersupply		Acual	0.75	0.25				0.5
		Connect to Escape Keeper Cable Set		Actual	1	0.25			0.75
		Mount & Secure		Actual	0.75	0.25		0.5
				Remaining	0	0	0	0	0	0	0

Room 1	Control Desk			Forecast	21.25	4.25	0	13	1	2.5	0.5
		Design Base and Discuss Plan		Actual	2	2
		Assemble Base and Prepare Desk Top		Actual	4.25	0.25		4
		Build Console Housing		Actual	2.25	0.25		2
		Finish and Trim Consoles, Box in corner		Actual	3.25	0.25		2		1
		Design Housing for Security Boxes		Actual	2.75	0.25		2		0.5
		Close in base assembly		Actual	2.25	0.25		2
		Install LED Light Panels x2		Actual	1.25	0.25			1
		Cut and install Pegboard		Actual	0.25	0.25				TODO
		Install Speaker		Actual	0.25	0.25				TODO
		Test		Actual	0
				Remaining	2.75	0.25	0	1	0	1	0.5

Room 2	Control Desk			Forecast	28.25	2.25	0.5	3.5	0	22	0
		Design Base and Discuss Plan		Actual	0.25	0.25
		Assemble Base and Prepare Desk Top		Actual	1.25	0.25		1
		Build Console Housing		Actual	0.75	0.25		0.5
		Add Pegboard and Housings		Actual	10.25	0.25				10
		Cut and Install Openings for Screens & puzzle		Actual	6.25	0.25		2		4
		Install Digital Keypad		Actual	4.75	0.25	0.5			4
		Install 2 Key Switches		Acual	2.25	0.25				2
		Mount Telephone Prop		Actual	1.25	0.25				1
		Install Speaker		Actual	0.25	0.25				TODO
				Actual	0
				Remaining	1	0	0	0	0	1	0

Room 2	Telephone Prop			Forecast	5.5	1.5	2.75	0.5	0.25	0.5	0
		Examine Prop and MP3 Card		Actual	2.5	0.5	2
		Reassemble and Test Operation		Actual	0.75	0.25	0.25	0.25
		Install 12V Power Supply and Power		Actual	0.75	0.25				0.5
		Connect Prop to Cable Set		Actual	0.75	0.25		0.25	0.25
		Reprogram (Unknown)		Acual	0.25	0.25
		Test		Actual	0
				Remaining	0.5	0	0.5	0	0	0	0

Room 1	Patch Panel			Forecast	7.5	2	0.5	3	0.5	1.5	0
		Design & Build Box		Actual	1.5	0.5		1
		Cut and Install Interior Panel		Actual	1.75	0.25		1.5
		Cut and Install 2 Doors		Actual	0.75	0.25		0.5
		Install Patch Panel in Interior Panel		Actual	0.75	0.25				0.5
		Connect to Cable Set		Actual	0.75	0.25			0.5
		Connect to 5VDC Power Supply		Actual	1.25	0.25				1
		Reprogram Device		Actual	0.25	0.25	TODO
				Remaining	0.5	0	0.5	0	0	0	0

Room 1	Game Master TV Console			Forecast	8.75	1.75	0	3	1.5	2.5	0
		Design and Build Box		Actual	1.5	0.5		1
		Cut Panel		Actual	1.25	0.25		1
		Cut hole for monitor and drill holes for leds		Actual	0.75	0.25		0.5
		Install 8 LED Indicators		Actual	0.75	0.25		0.5
		Connect to Cable Set x2		Actual	3.75	0.25			1.5	2
		Mount TV and Connect HRMI		Actual	0.25	0.25				TODO
		HDMI Cable		Parts Req	0
				Remaining	0.5	0	0	0	0	0.5	0

Room 1	Security Monitor			Forecast	8.5	2	0	2	2.5	1	1
		Design & Build Box		Actual	1.25	0.25		1
		Cut Panel		Actual	1.25	0.25		1
		Connect to Cable Set		Actual	0.75	0.25			0.5
		Connect to Power Set CAT5		Actual	1.25	0.25			1
		Connect Camera to ViD & POWER		Actual	1.25	0.25			1
		Mount Monitor to Panel		Actual	1.25	0.25				1
		Repair Monitor		Actual	1.5	0.5					1
				Remaining	1	0	0	0	0	0	1

Room 2	Security Camera Puzzle			Forecast	6.5	1		5	0.5	0	0
		Mount Three Dials in Counter		Actual	4.25	0.25		4
		Connect Camera to Cable Set		Actual	0.5	0.25			0.25
		Mount Camera		Actual	0.5	0.25		0.25
		Install LED Panel and connect to Cable Set		Acual	0.75	0.25		0.25	0.25
				Remaining	0.5	0	0	0.5	0	0	0

Room 1	Key Card Readers x2			Forecast	9.75	2.25	0.5	4	3	0	0
		Mount Key Card Readers		Actual	2.25	0.25		2
		Design and Cut 2 Templates		Actual	3	1		2
		Connect to Cable Sets x2		Actual	1.5	0.5			1
		Install x4 RJ45 Connectors		Acual	2.25	0.25			2
		Program Reader		Actual	0.25	0.25	TODO
		Test		Actual	0
				Remaining	0.5	0	0.5	0	0	0	0

Room 2	27CH DMX LED CONTROLLER			Forecast	7	3	1	2	1	0	0
		Mount & Secure Controller		Actual	2.25	0.25		2
		Connect Cont. to 12VDC Power Supply		Actual	0.75	0.25			0.5
		Connect to !2VDC BATTERY BANK (FUTURE)		Acual	0.25	0.25			TODO FUTURE
		Connect 6 Button LED to Cont.		Actual	0.25	0.25
		Connect 8 Switch LED Display to Cont.		Actual	0.25	0.25
		Connect 13 LED White Panels to Cont.		Actual	0.25	0.25
		Configure Device in Flexmax Firmware		Actual	2	1	1
		Build RJ45 to XLR adapter for DMX		Actual	0.5	0.5					TODO
				Remaining	0.5	0	0	0	0.5	0	0

Room 1	Dual Doors with Mag Lock			Forecast	8	1.5		4.5	0.5	1.5	0
		Remove sliding door & mechanisim		Actual	1.25	0.25		1
		Remove material surrounding door frame		Actual	1.25	0.25		1
		Connect to Cable Set		Acual	1.25	0.25			0.5	0.5
		Design and cut dual doors		Actual	0.75	0.25		0.5
		Install Doors with piano hinge		Actual	1.25	0.25		1
		Install Magnet and plate		Actual	1.25	0.25				1
		Finish Trim		Actual	0			TODO
		Test		Actual	0
				Remaining	1	0	0	1	0	0	0

Room 2	7 Button Puzzle			Forecast	9.5	2.5	0.5	3	2.5	1
		Prep & Review Tech Puzzle		Actual	0.5	0.5
		Connect 7 buttons to Cable Set		Actual	1	0.25			0.75
		Connect LED Lights to 27CH Controller		Acual	1	0.25			0.75
		Connect Display to Control Board		Actual	1.25	0.25			1
		Design console for buttons		Actual	1.75	0.25		1.5
		Install Buttons into Faceplate		Actual	1.25	0.25				1
		Program device		Actual	0.25	0.25	TODO
		Cut hole for display		Actual	1.25	0.25		1
		Mount and secure display in console		Actual	0.75	0.25		0.5
				Remaining	0.5	0	0.5	0	0	0	0

Room 2	8 Clock Dial Puzzle			Forecast	5	1.5	1	1.25	0.25	0	1
		Review operation of device		Actual	0.75	0.25	0.5
		Cut hole in control panel and secure device		Actual	1.25	0.25		1
		Connect output to cable set and test connection		Acual	0.5	0.25			0.25
		Connect 5VDC power supply to 110V		Actual	0.5	0.25		0.25
		Reprogram device		Actual	0.25	0.25	TODO
				Actual	0
		Repair power connection - device intermittnet		Actual	1.25	0.25					1
				Actual	0
				Remaining	0.5	0	0.5	0	0	0	0

Room 1	Key Pad x3			Forecast	20.75	3.5	0.75	9	4	3	0.5
		Build up surface in console for keypad x3	Done	Actual	4.25	0.25		4
		Mount & Secure Key Pad x3	Done	Actual	2.75	0.75		2
		Install & Connect to 12VDC power supply x3	Done	Acual	2	0.5			1.5
		Connect to Cable Set x3	Done	Actual	1	0.5			0.5
		Reprogram security code	TODO	Actual	1	0.25	0.75
		Install Magnets x3	Done	Actual	2.5	0.5				2
		Connect to Magnets x3	Done	Actual	2	0.5			1.5
		Design & Build Magnetic Drop Bin (Middle Compartment)	Done	Actual	5.25	0.25		3	0.5	1	0.5
		Test	TODO	Actual	0	0
				Remaining	0	0	0	0	0	0	0

Room 2	Escape Keeper			Forecast	5	1.5	1	1	1	0	0.5
		Mount and secure to wall	Done	Actual	1.25	0.25		1
		Connect Input 5,6,7 and common to Key Pads in room 1	Done	Actual	0.75	0.25			0.5
		Add audio mp3 clips		Acual	0.25	0.25
				Actual	0
				Actual	0
				Actual	0
				Actual	0
		test		Actual	0						TODO
				Remaining	2.75	0.75	1	0	0.5	0.5	0

Room 1	8 Switch Panel			Forecast	5.5	1.5	0.5	1	2	0.5	0
		Cut Hole, Mount & Secure Switches in left console		Actual	1.75	0.25		1		0.5
		Prep and Review Tech Puzzle		Actual	0.25	0.25
		Program Device		Acual	0.25	0.25	TODO
		Connect to Cable Set & Network Cable		Actual	0.75	0.25			0.5
		Connect to 5VDC Power		Actual	0.75	0.25			0.5
				Actual	0
		Repair Display		Actual	1.25	0.25			1
				Actual	0
				Remaining	0.5	0	0.5	0	0	0	0

Room 1	8 LED Display			Forecast	5	1.25	1	1.25	1	0.5
		Cut Hole, Mount & Secure Display in right console		Actual	1.5	0.25		0.75		0.5
		Prep and Review Tech Puzzle		Actual	0.25	0.25
		Connect to 5VDC Power		Acual	1.25	0.25		0.5	0.5
		Connect to Cable Set		Actual	0.75	0.25			0.5
				Actual	0
		Fix wiring on device		Actual	1.25	0.25	1
				Actual	0
				Actual	0
				Remaining	0	0	0	0	0	0	0

Room 2	Screen & Key Switches			Forecast	5.75	1.25	0	3	1.5	0	0
		Install two key switches		Actual	1.75	0.25		1.5
		Connect both switches to Cable set		Actual	0.75	0.25			0.5
		Cut hole in console for two screens		Acual	1.25	0.25		1
		Secure both screens		Actual	0.75	0.25		0.5
		Connect screens to cable set		Actual	1.25	0.25			1
				Actual	0
				Actual	0
				Actual	0
				Remaining	0	0	0	0	0	0	0

Room 1	Relay Board 4CH #3	Relay Board for Key Switch		Forecast	3	1	0	0.5	1	0.5	0
		Set-Up 4CH Relay Board #1 Controller		Actual	0.75	0.25			0.5
		Power Controller 12VDC Powersupply		Acual	0.75	0.25				0.5
		Connect to Escape Keeper Cable Set		Actual	0.75	0.25			0.5
		Mount & Secure		Actual	0.75	0.25		0.5
				Remaining	0	0	0	0	0	0	0

Room 1 & 2	Install Wire Chase			Forecast	5	1				4
		Install WIre Chase Security Monitor		Actual	1.25	0.25				1
		Install Wire Chase Control Desk Room 1		Acual	0.25	0.25
				Actual	0
				Actual	0
				Remaining	3.5	0.5	0	0	0	3	0

Room 1 & 2	Install LED Lighting			Forecast	6.5	1			1.5	4
		Install 2 LED Room 1 Control Desk		Actual	2.25	0.25			0.5	1.5
		Install 2 LED Room 2 Control Desk		Acual	2.25	0.25			0.5	1.5
		Installed Portait LED Room 1		Actual	1.25	0.25				1
		Install Portent LED Room 2 x2		Actual	1.75	0.25				1.5
				Actual	0
				Actual	0
				Actual	0
				Actual	0
				Remaining	-1	0	0	0	0.5	-1.5	0

## PR Timeline
		Forecast	Time Spent	Remaining

Room 1	Console	21.25	18.5	2.75
Room 1	Relay Board 4CH #2	2.75	2.75	0
Room 1	Color Bar Screen	12	12	0
Console 1B	Radar Screen	19.5	19.5	0
Console 1	Relay Board 4CH #1	2.5	2.5	0
Room 1	8 Dial Clock Puzzle	5	4.5	0.5
Room 1	8 Switch Panel	5.5	5	0.5
Room 1	8 Switch Display	5	5	0
Room 1	Patch Panel	7.5	7	0.5
Room 1	Game Master TV Console	8.75	8.25	0.5
Room 1	Security Monitor	8.5	7.5	1
Room 2	Security Camera Puzzle	6.5	6	0.5
Room 1	Key Card Readers x2	9.75	9.25	0.5
Room 1	Dual Doors with Mag Lock	8	7	1
FLEX	Flexmax 2 Show Controller	39.5	37.75	1.75
Room 2	27CH DMX Controller	7	6.5	0.5
Room 2	Telephone Prop	5.5	5	0.5
Room 2	Control Desk	28.25	27.25	1
Room 2	7 Button Puzzle	9.5	9	0.5
Room 2	Screen & Key Switches	5.75	5.75	0
Room 2	Relay Board 4CH #3	3	3	0
Room 1	Key Pad x3	20.75	20.75	0
Room 2	Escape Keeper	5	2.25	2.75
Room 1 & 2	Install Wire Chase	5	1.5	3.5
Room 1	Install LED Lighting	6.5	7.5	-1

	Estimate Totals	258.25	241	17.25

## Game Time
Kit	Prop	Desc		Status	Type		Design Time	Application Time	Station Prep	Cable Set	Installation	Testing & Drag.		Feb 10		Feb 11		Feb 12		Feb 13		Feb 14		Feb 15	Feb 16		Feb 17		Feb 18	Feb 19		Feb 20		Feb 21	Feb 22		Feb 23		Feb 24	Feb 25		Feb 26		Feb 27	Feb 28		Feb 29		Mar 1	Mar 2		Mar 3		Mar 4	Mar 5		Mar 6		Mar 7	Mar 8		Mar 9		Mar 10	Mar 11		Mar 12		Mar 13	Mar 14		Mar 15		Mar 16	Mar 17		Mar 18		Mar 19	Mar 20		Mar 21		Mar 22	Mar 23		Mar 24		Mar 25	Mar 26		Mar 27		Mar 28	Mar 29

FLEX	Flexmax 2 Show Controller				Forecast	14	6	2	2.5	2.5	1	0
		Mount & Secure		Complete	Actual	3	0.5		2		0.5
		Install 12VDC 5AMP Powersupply		Complete	Actual	0.75	0.25				0.5
		Connect Input #1			Actual	0.5	0.25			0.25
		Connect Input #2			Actual	0.5	0.25			0.25
		Connect Input #3			Actual	0.5	0.25			0.25
		Connect Input #4			Actual	0.5	0.25			0.25
		Connect Inout #5			Actual	0.5	0.25			0.25
		Connectr Input #6			Actual	0.25	0.25
		Connect Input #7			Actual	2.25	0.5	1	0.5	0.25
		Connect Input #8			Actual	0.5	0.25			0.25
		Connect DMX OUT (RJ45)			Actual	0.25	0.25
		Build RJ45 Adapter			Actual	0.25	0.25
		Insert MP3 Audio Tracks			Actual	0.25	0.25
		Connect Audio Speakers			Actual	0.25	0.25
		Program Scenes			Actual	2	2	TODO
		Test Equipment			Actual	0						TODO
					Remaining	1.75	0	1	0	0.75	0	0

Game Master	Control Console	Task/Issue	Specificatoins		Forecast	15.25	2.75		5.5	1	5	1
		Build Console		Compelete	Actual	1.25	0.25		1
		Chase 3x CAT5 to Rafters (stripped)	CATS 5, 3x runs (4 pair/run)	Complete	Acual	1.25	0.25				1
		Install 9 Buttons	9x microswitches NO/COM	Compelete	Actual	0.75	0.25		0.5
		Connect Buttons to terminals & contacts	36x terminals, 14x contacts	Compelete	Actual	0.75	0.25		0.5
		Connect Game Time Event Terminals to Cable set		Compelete	Actual	1.25	0.25			1
		Ad Remote button for Medicine Cabinate		Complete	Actual	0.75	0.25		0.5
		Rafters - Connect Cable Set to Game Time		In Prograss	Actual	1.25	0.25		1
		Raters - Connect Power Solenoid to battery bank		Completed	Actual	0.75	0.25				0.5
		Rafters - Install 12VDC 4CH Relay		In Progress	Actual	2.75	0.25				2.5
		Add REMOTE Button to Door to Open TNT		Completed	Actual	2.25	0.25		1		1
		Add remote for stick puzzle		ToDO	Actual	0.25	0.25
		Test & DIag		Completed	Actual	1						1
					Remaining	1	0	0	1	0	0	0

Hidden Gear Puzzle	Helmet Box				Forecast	2.5	0.5				2
		Install 2A Soloind		Issue	Actual	0					TODO
		Run12VDC / RELAY		Issue	Acual	0.25	0.25				TODO
					Actual	0	TODO
					Actual	0
					Actual	0
						0
					Actual	0
					Actual	0
					Actual	0
						0
						0
					Remaining	2.25	0.25	0	0	0	2	0

Hidden Gear Puzzle	Game Console				Forecast	2.25	0.25				2
		Update UNO & NANO Code		Issue	Actual	0.25	0.25				TODO
					Acual	0
					Actual	0
					Actual	0
					Actual	0
						0
					Actual	0
					Actual	0
					Actual	0
						0
						0
					Remaining	2	0	0	0	0	2	0

Game Master	12V Battery Bank				Forecast	4	1				3
		Move Battery Bank in Rafters		Issue	Actual	0.75	0.25				0.5
		Place 2x 30A 10Guage Cable			Acual	1.25	0.25				1
		Source parts (rona)			Actual	0.75	0.25				0.5
						0
		Connect to Power Grid			Actual	1.25	0.25				1
						0
						0
						0
						0
						0
						0
					Remaining	0	0	0	0	0	0	0

## Forecast
		Forecast	Time Spent	Remaining	Status	March 7~13	March 14~20	March 7	March 8	March 9	March 10	March 11	March 12	March 13	March 14	March 15	March 16	March 17	March 18	March 19	March 20	March 21	March 22	March 23	March 24	March 25	March 26	March 27	March 28	March 29	March 30	March 31	April 1	April 2	April 3
						Week Total	Week Total	Thur	Fri	Sat	Sun	Mon	Tues	Wed	Thur	Fri	Sat	Sun	Mon	Tues	Wed	Thur	Fri	Sat	Sun	Mon	Tue	Wed	Thur	Fri	Sat	Sun	Mon	Tues	Wed
		270.75	250.75	20			41							7	8	5.5	0	5.75	6.5	10.25	5	6.5	5	0	4.5	6	5	0	5	0.75	0	8	5	5.5
Per Diem - Travel															$25.00

Game Time

Game Master	Control Console	15.25	14.25	1	Ports Req									7	4	3				1
Hidden Gear Puzzle	Helmet Box	2.5	0.25	2.25	Scheduled		Install Solonoid													2.25
Hidden Gear Puzzle	Game Console	2.25	0.25	2	Issue		Update Code													2
Game Master	12V Battery Bank	4	4	0	Completed		Set-Up Battery Bank								4
			0
			0

	Estimate Totals	24	18.75	5.25			16.25								8	3	0	0	0	5.25	0	0

Presidents Big Mistake

Room 1	Console	21.25	18.5	2.75	Scheduled		Install Pegboard, LEDs																											2.75
Room 1	Relay Board 4CH #2	2.75	2.75	0	Completed		-
Room 1	Color Bar Screen	12	12	0	Parts Req		4GB SD Card								PARTS	PARTS									4								5
Console 1B	Radar Screen	19.5	19.5	0	Scheduled		Parts																1									8
Console 1	Relay Board 4CH #1	2.5	2.5	0	Completed		-
Room 1	8 Dial Clock Puzzle	5	4.5	0.5	Issue		Intermittent Power																			1
Room 1	8 Switch Panel	5.5	5	0.5	Scheduled		Connect Cable Sets																											2.75
Room 1	8 Switch Display	5	5	0	Issue		Repair Connections
Room 1	Patch Panel	7.5	7	0.5	Scheduled		Reprogram Device
Room 1	Game Master TV Console	8.75	8.25	0.5	Parts Req		HDMI Cable								PARTS	PARTS
Room 1	Security Monitor	8.5	7.5	1	Issue		Repair Monitor											1	1
Room 2	Security Camera Puzzle	6.5	6	0.5	Scheduled		Install Dials x3												1.5	0.5		2
Room 1	Key Card Readers x2	9.75	9.25	0.5	Scheduled		Reprogram Device													2
Room 1	Dual Doors with Mag Lock	8	7	1	Scheduled		Install Doors & maglock											3.25
FLEX	Flexmax 2 Show Controller	39.5	37.75	1.75	Scheduled													0.5	0.5		4	4	2		0.5	1.5	5		5	0.75
Room 2	27CH DMX Controller	7	6.5	0.5	Parts Req		RJ45 Adapter to DMX												0.5
Room 2	Telephone Prop	5.5	5	0.5	Scheduled														0.5		0.5
Room 2	Control Desk	28.25	27.25	1	Scheduled																	0.5
Room 2	7 Button Display	9.5	9	0.5	Scheduled		Install Buttons									2.5				2
Room 2	Screen & Key Switches	5.75	5.75	0	Completed
Room 2	Relay Board 4CH #3	3	3	0	Scheduled		Install Relay											1	2
Room 1	Key Pad x3	20.75	20.75	0	Completed																		2			3.5
Room 2	Escape Keeper	5	2.25	2.75	Scheduled		Update MP3's								SD CARD	SD CARD			0.5	0.5	0.5
Room 1 & 2	Install Wire Chase	5	1.5	3.5	Scheduled														1											1.5
Room 1	Install LED Lighting	1.25	7.5	-1	Scheduled																									3
			0
	Estimate Totals	246.75	232	14.75			24.75								0	2.5	0	5.75	6.5	5	5	6.5	5	0	4.5	6	5

Week 1	Feb 1	Feb 7	$1,000.00
Week 2	Feb 8	Feb 14	$1,000.00
Week 3	Feb 15	Feb 21	$1,000.00
Week 4	Feb 22	Feb 28	$1,000.00
Week 5	Feb 29	Mar 6	$1,000.00
Week 6	Mar 7	Mar 13	$1,000.00
Week 7	Mar 14	Mar 20	$1,000.00	$0.00

## PBM Seq
Electronic Sequence

	Step One	Step Two	Step Three	Step Four	Step Five	Step Six	Step Seven	Step Eight	Step Nine	Step Ten	Step Eleven	Step 12AB	Step 13	Step 14	Step 15
	Open Left Box Room #1	Levers Puzzle	Folders Puzzle	Radar Puzzle	Enter Control Room	Coordinates Puzzle	Power Puzzle	Discs Puzzle			Buttons Puzzle	Launch Code	Telephone Puzzle	Keypad	Stop Launch & Win
	Digital Keypad Left	Toggle Switchs	Turn Dials	Digital Keypad Right	Insert Cards	PADLOCK	Insert Cable	Turn Dials			Digital Keypad Middle	Two Key Switches	Enter Phone Number	Enter Code from Map	Press button
	5182#	GGRGRGGR	Match Clocks	1314#	#2, #4	693	Follow Order	984			4709#	6281,0237		14852	-
	Retrieve KeyCard 1 Commanding Officer	Color Bar Monitor Turns On	Radar Screen Turns On	Retreive Key Card #2	Doors Open	Retrieve Cables	Show Clue Discs Puzzle	Green Key			Reveal opening for endoscope	Retrieve top secret folder	Listen to message	Open Box	Door unlocks

	Escape Keeper	Flexmax	Flexmax	Flexmax	Flexmax		Flexmax				Escape Keeper	Escape Keeper	Escape Keeper	Flexmax	Flexmax
	Input	Input	Input	Input	Input		Input				Input		Input	Input	Input
	EK#5	FM#8	FM#7		FM#2		FM#6				#6			#5
	Output	Output	Output	Output					EK#6
			FM#9					Output
					#1
	Escape Keeper	Output	Flexmax	Output

1			2 Cards Inserted	EXIT
2			not used	Open Command Center
3			Escape Keeper
4
5	Open Left Box
6	Open Middle Box		Turn Color Bar Monitor On
7	Open Right Box > Flexmax		Turn Radar Monitor On
8
9				Turn on Radar
10				Turn on Color Monitor
11
12
13				Portrait Light RM1
14
15
16